train track

DEVELOPMENT PLAN & TECHNICAL ROADMAP

From Prototype to Production

Cross-Platform Fitness Coaching Application

iOS · Android · Web

Stack: React Native + Expo SDK 53 + Supabase + TypeScript

Development: AI-Assisted (Claude Code + Cursor)

Version 1.0 — March 2026

# 1. Executive Summary

This document translates the Train Track blueprint into an actionable 24-week development plan organized into six phases. Each phase has clear deliverables, acceptance criteria, and estimated timelines optimized for AI-assisted solo development using Claude Code and Cursor.

The plan is structured around one core principle: ship the smallest thing that proves the value proposition, then iterate. For Train Track, that means the coach workout builder and client logging experience come first — everything else layers on top.

Target MVP launch: Week 12 (internal beta) → Week 16 (public beta) → Week 20 (App Store/Play Store)

Total pre-launch budget: $3,500–$6,000 (infrastructure + legal + tools)

Monthly operating cost at launch: $150–$300

# 2. Development Phases Overview

The 24-week roadmap is divided into six phases, each building on the previous:

| Phase | Name | Weeks | Goal |
| --- | --- | --- | --- |
| 0 | Foundation | 1–2 | Monorepo, auth, database, navigation shell |
| 1 | Coach Core | 3–6 | Workout builder, program management, client management |
| 2 | Client Core | 7–10 | Workout viewing, set logging, PR tracking, timers |
| 3 | Communication & Polish | 11–12 | Messaging, notifications, offline mode, bug fixes |
| 4 | Beta & Iteration | 13–16 | TestFlight/Play beta, feedback loops, performance |
| 5 | Launch & Growth | 17–24 | Store submission, marketing, V1.1 features |

PHASE 0: Foundation  —  Weeks 1–2

Set up the entire development environment, monorepo structure, authentication, database schema, and navigation shells for both coach and client interfaces.

## 3.1 Monorepo & Tooling Setup

Initialize the Turborepo monorepo with pnpm workspaces. This structure is critical for AI-assisted development — Claude Code and Cursor work best when they can see the full codebase context.

Project Structure

train-track/ (root)

- CLAUDE.md — AI coding instructions (stack rules, conventions, forbidden patterns)

- .cursor/rules/react-native.mdc — Cursor-specific RN rules

- turbo.json — Turborepo pipeline config

- apps/mobile/ — Expo app (iOS + Android + Web via Expo Router)

- packages/shared/ — TypeScript types, constants, validation schemas (Zod)

- packages/ui/ — Shared UI component library (NativeWind)

- supabase/ — Migrations, edge functions, seed data, RLS policies

CLAUDE.md Critical Rules

These rules prevent the most common AI-generated errors in React Native projects:

- NEVER use HTML tags (div, span, p) — only React Native primitives (View, Text, Pressable)

- Use NativeWind className for styling, not StyleSheet.create

- Use Expo Router file-based routing, not React Navigation directly

- Use @expo/vector-icons, not lucide-react or react-icons

- Use react-native-reanimated for animations, not framer-motion

- All API calls go through packages/shared/api/ — never inline Supabase queries in components

- Store weights in kg internally; convert on display per user preference

## 3.2 Supabase Backend Setup

Database Schema (Core Tables)

| Table | Key Columns | Purpose |
| --- | --- | --- |
| users | id, email, role (coach/client), name, avatar_url, unit_pref | All users with role-based access |
| coach_clients | coach_id, client_id, status, invited_at, accepted_at | Coach-client relationships |
| programs | id, coach_id, name, description, type, image_url | Training programs/cycles |
| program_assignments | program_id, client_id, start_date, status | Which client has which program |
| workout_templates | id, program_id, day_number, title, notes | Coach-designed workout blueprints |
| template_sections | id, workout_template_id, letter (A/B/C), title, format (sets/AMRAP/EMOM/fortime), settings_json | Workout sections with format metadata |
| template_exercises | id, section_id, exercise_id, order, sets, reps, weight_kg, percentage_1rm, rpe, rest_sec, notes | Prescribed exercises within sections |
| exercises | id, name, description, category, video_url, created_by | Global + coach-custom exercise library |
| workout_logs | id, client_id, workout_template_id, date, status (complete/partial/missed), comment, duration_sec | Client workout completions |
| logged_sets | id, workout_log_id, template_exercise_id, set_number, reps, weight_kg, rpe, notes, timestamp | Actual performed sets |
| personal_records | id, client_id, exercise_id, weight_kg, reps, estimated_1rm, achieved_at, auto_detected | PR history with auto-detection |
| injuries | id, client_id, name, area, date, status, avoid, notes | Injury and limitation tracking |
| skills | id, client_id, name, status (locked/in-progress/blocked), current_level, notes | Skill progression tracking |
| messages | id, sender_id, recipient_id, workout_log_id, content, read_at | Coach-client messaging |
| videos | id, coach_id, title, url, category, exercise_id | Video library entries |

Row Level Security (RLS) Policies

These policies enforce multi-tenant data isolation at the database level:

- Coaches see only their own clients, programs, and workout templates

- Clients see only programs assigned to them and their own logs/PRs

- Messages visible only to sender and recipient

- Exercise library: global exercises visible to all; coach-created exercises visible only to that coach and their clients

PR Auto-Detection Trigger

A PostgreSQL trigger on logged_sets INSERT that calculates estimated 1RM (Epley formula: weight × (1 + reps/30)) and compares against existing personal_records for that client+exercise combination. If new record, insert into personal_records with auto_detected = true and fire a Supabase Realtime event for the celebration animation.

## 3.3 Authentication & Navigation Shells

- Supabase Auth with email/password + Google OAuth + Apple Sign-In

- Role-based routing: coach role → /coach/* layout (sidebar nav), client role → /client/* layout (bottom tabs)

- Coach navigation shell: Dashboard, Programs, Clients, Library, PR Tracker, Injuries, Profile

- Client navigation shell: Train (home), Track (progress), Profile

- Theme system: dark mode default for client, light mode default for coach, toggle in Profile

Phase 0 Deliverables

| Deliverable | Acceptance Criteria |
| --- | --- |
| Monorepo builds on all platforms | npx expo start --web, --ios, --android all launch without errors |
| Auth flow complete | Sign up, sign in, sign out, password reset working on all platforms |
| Database schema deployed | All 15 tables created with RLS policies, seed data loaded |
| Navigation shells render | Coach sidebar and client bottom tabs navigate between empty screens |
| CLAUDE.md verified | Claude Code generates correct RN components (no HTML, correct imports) |

PHASE 1: Coach Core  —  Weeks 3–6

Build the coach-side features that are essential before any client can use the app. The workout builder is the #1 priority — it is the product.

## 4.1 Workout Builder (Weeks 3–4)

This is Train Track’s primary differentiator. The builder must natively support CrossFit workout formats that competitors handle poorly or not at all.

Supported Workout Formats

| Format | Description | Settings | Scoring |
| --- | --- | --- | --- |
| Straight Sets | Traditional sets × reps | Sets, reps, weight/%, RPE, rest | Weight × reps |
| Superset / Circuit | Multiple exercises grouped | Rounds, rest between rounds | Completion |
| AMRAP | As Many Rounds As Possible | Time cap (minutes) | Rounds + reps |
| EMOM | Every Minute On the Minute | Minutes, exercises per minute | Completion / load |
| For Time | Complete work ASAP | Time cap, movements + reps | Time (mm:ss) |
| Tabata | 20s work / 10s rest | Rounds, exercises | Reps per round |

Builder UX Requirements

- Freeform text entry WITH structured data — coaches can type workout descriptions naturally but the system parses sets/reps/weight into structured fields for tracking

- Drag-and-drop reordering of sections (A, B, C) and exercises within sections

- Copy entire workouts or sections across days, weeks, and clients

- Exercise autocomplete pulling from the exercise library with inline video preview

- Percentage-based fields that auto-calculate from each client’s 1RM (“@70% 1RM” shows as “105 kg” for a client with 150 kg back squat)

- Injury warnings: if a prescribed exercise conflicts with a client’s logged injury, show a yellow warning with suggested alternatives

## 4.2 Program Management (Week 5)

- Create programs with name, description, type (Template/Ongoing/Standard), and optional image

- Calendar view: assign workout templates to specific dates within a program

- Assign programs to individual clients or groups of clients

- Program templates: save a complete multi-week program and apply it to new clients with one click

- Progress tracking per program: see which clients are on track, behind, or ahead

## 4.3 Client Management (Week 5–6)

- Client list with search, filter (Active/Pending/Archived), and sort

- Invite client by email — triggers Supabase edge function to send invitation email

- Client detail view: profile info, assigned programs, PR history, injury notes, compliance rate

- Batch operations: assign program to multiple clients, send message to group

## 4.4 Exercise Library (Week 6)

- Seed with 200+ CrossFit/functional fitness exercises (name, description, muscle groups, equipment)

- Coach can add custom exercises with description and video links (YouTube/Vimeo embed)

- Category filtering: Olympic Lifting, Gymnastics, Conditioning, Strength, Accessory

- Video Library tab: manage all video links with search and categorization

Phase 1 Deliverables

| Deliverable | Acceptance Criteria |
| --- | --- |
| Workout builder | Can create workouts in all 6 formats with exercises, sets, reps, weight/%, rest |
| Program CRUD | Create, edit, delete programs; assign to clients; calendar scheduling |
| Client management | Invite, list, filter, view detail, archive clients |
| Exercise library | 200+ seeded exercises; coach can add custom; video embed works |
| Copy/paste workflows | Copy workout to another day/client in under 3 clicks |
| Injury warning system | Yellow warning appears when assigning exercise that conflicts with client injury |

PHASE 2: Client Core  —  Weeks 7–10

Build the client mobile experience. Every design decision is measured by one question: can a sweaty person in a loud gym use this in under 3 taps?

## 5.1 Train Tab — Workout View & Logging (Weeks 7–8)

Daily Workout View

- Welcome header with avatar, name, notification bell

- Horizontal weekly calendar strip with swipe navigation (matching the prototype)

- Collapsible program accordions showing assigned workout for selected date

- Empty state illustration when no workout is assigned

- Daily progress ring showing completed/total sections

Workout Section Cards

- Section label (A, B, C) with title, expand/collapse chevron, completion toggle

- Expanded view: full workout description with exercise details

- Inline exercise demo video thumbnails (tap to play without leaving the screen)

- Built-in timers per format: countdown for AMRAP/ForTime, interval beeps for EMOM/Tabata, rest timer between sets

- Timer persists when app is backgrounded with audio/haptic alerts

Set-by-Set Logging

- Each exercise shows previous performance as default (auto-populated from last session)

- Tap weight/reps fields to edit; keyboard opens with numeric pad

- Swipe right on a set to mark complete; swipe left to skip

- Auto-start rest timer after marking a set complete

- Plate calculator: tap weight field → shows plates needed on each side of the bar (configurable bar weight and available plates)

- AMRAP scoring: rounds + reps input with stopwatch

- For Time scoring: manual or auto-stop timer

- Log detail screen: optional notes text field + file/photo upload + submit button

- Validation toast if required fields are empty

- Mark as missed option

## 5.2 PR Tracking & Celebrations (Week 9)

- Auto-detection via database trigger when a logged set exceeds previous PR

- Confetti animation + haptic feedback + celebratory sound on PR

- PR history view per exercise showing progression over time

- Estimated 1RM calculation (Epley formula) for each exercise

- PR cards on the Track tab showing all-time bests with kg/lb toggle

- Coach receives notification when client hits a PR

## 5.3 Track Tab — Progress Overview (Week 9–10)

- Program progress bars: completed/total exercises per program (matching prototype)

- Skills to Unlock checklist: locked/in-progress/blocked status with progression notes

- 1RM trend charts per exercise (line graph over time)

- Training volume chart (total weight moved per week)

- Compliance rate: workouts completed vs. assigned over past 4 weeks

- Body metrics section: weight log with chart, body measurements, progress photos

## 5.4 Offline Mode (Week 10)

Poor gym WiFi is universal. The client app must work offline for core logging functionality.

- Cache today’s workout and exercise library on app open

- Log sets locally when offline using Zustand persisted store

- Sync queue: when connection resumes, push all queued logs to Supabase

- Visual indicator showing offline status and pending sync count

- Conflict resolution: server wins for workout templates, client wins for logged data

Phase 2 Deliverables

| Deliverable | Acceptance Criteria |
| --- | --- |
| Workout view | Client sees assigned workout for any date with proper formatting per workout type |
| Set-by-set logging | Can log weight × reps for every set, previous performance auto-populated |
| Built-in timers | AMRAP countdown, EMOM intervals, rest timer all work including background mode |
| PR auto-detection | New PR triggers confetti + notification to coach within 5 seconds |
| Track tab charts | 1RM trends, volume chart, compliance rate all render with real logged data |
| Offline logging | Can log full workout without network; syncs when reconnected |
| 3-tap test | Any set can be logged in ≤3 taps from the Train tab |

PHASE 3: Communication & Polish  —  Weeks 11–12

Connect coach and client with messaging and notifications. Polish the entire app for beta.

## 6.1 Messaging System

- 1-on-1 real-time messaging between coach and client (Supabase Realtime subscriptions)

- Workout-specific comments: client can leave a comment on a specific workout log that the coach sees in context

- Coach sees threaded conversation per client with workout log attachments

- Read receipts and typing indicators

## 6.2 Push Notifications

- Expo Push Notifications via Supabase Edge Functions

- Triggers: new workout assigned, new message, client completed workout, client hit PR, client missed workout

- Coach daily digest: summary of client activity (configurable time)

- Client reminders: configurable workout reminder time

## 6.3 Injury & Limitation Management

- Coach can log injuries per client: name, body area, date, status (active/recovering/resolved), movements to avoid, doctor’s notes

- Client can view their own injury notes

- Cross-references with workout builder: flagged exercises show yellow warning

- Injury status visible on client detail card in coach dashboard

## 6.4 UI/UX Polish Sprint

- Loading skeletons for all data-heavy screens

- Pull-to-refresh on all list views

- Smooth page transitions using react-native-reanimated shared element transitions

- Haptic feedback on key interactions (set completion, PR, timer alerts)

- Error states and empty states for all screens

- Accessibility audit: screen reader labels, minimum 44pt touch targets, color contrast ratios

- Performance audit: <2s cold start, <100ms interaction response, <16ms frame rendering

Phase 3 Deliverables

| Deliverable | Acceptance Criteria |
| --- | --- |
| Messaging | Real-time 1-on-1 chat works on all platforms; workout comments visible in context |
| Push notifications | All 5 trigger types fire correctly on iOS and Android |
| Injury management | Coach can CRUD injuries; warnings appear in workout builder |
| Polish | No loading jank, all empty/error states handled, passes accessibility audit |

PHASE 4: Beta & Iteration  —  Weeks 13–16

Get the app into real coaches’ and athletes’ hands. Iterate fast based on real-world gym usage.

## 7.1 Beta Distribution

- iOS: TestFlight via EAS Submit (up to 10,000 testers)

- Android: Google Play Internal Testing track via EAS Submit

- Web: Deploy coach dashboard to Vercel preview URL

- Target: 20–50 beta coaches with their real clients (100–300 total users)

## 7.2 Feedback Collection

- In-app feedback button (bottom of Profile screen) linking to short Typeform survey

- Dedicated Discord server with channels: #bugs, #feature-requests, #general, #coach-feedback, #athlete-feedback

- Weekly 15-minute video calls with 5 most active beta coaches

- PostHog analytics: track screen flows, drop-off points, feature usage frequency

- Sentry crash reporting with source maps for all platforms

## 7.3 E2E Testing with Maestro

Write Maestro YAML flows for critical user journeys:

- Coach creates a workout with AMRAP format and assigns to client

- Client opens workout, starts timer, logs 3 rounds + 7 reps, submits

- Coach views client’s submitted log with correct AMRAP score

- Client logs a set that triggers PR auto-detection

- Offline: client logs workout in airplane mode, reconnects, data syncs

## 7.4 Performance Optimization

- Measure and optimize: app size (<30MB), cold start (<2s), JS bundle size, memory usage

- Image optimization: exercise thumbnails served as WebP via Supabase Storage transforms

- List virtualization: FlashList for all long lists (exercise library, client lists, workout logs)

- Supabase query optimization: add indexes based on PostHog slow-query analysis

PHASE 5: Launch & Growth  —  Weeks 17–24

Ship to the App Store and Google Play. Execute the marketing plan. Begin building V1.1 features.

## 8.1 Store Submission (Weeks 17–18)

Pre-Submission Checklist

- Privacy Policy and Consumer Health Data Privacy Policy published on website

- Terms of Service with medical disclaimer published

- Apple Privacy Nutrition Labels completed in App Store Connect

- Google Play Data Safety section completed

- Google Play Health Apps declaration form submitted

- Account deletion functionality working

- App icons (1024×1024), screenshots (6.7", 6.5", 5.5" iPhones + iPad), and preview video created

- App Store description with ASO-optimized keywords

- Stripe integration for coach subscription billing tested in production mode

- RevenueCat configured for in-app subscription management

App Store Optimization (ASO)

Title: Train Track: Fitness Coaching

Subtitle: Program Builder for Coaches

Keywords: coaching app, workout programming, CrossFit, personal trainer, WOD tracker, fitness coach, AMRAP timer

Category: Health & Fitness

Screenshots: 6 screenshots showing: (1) Coach workout builder desktop, (2) Client daily workout view, (3) AMRAP timer in action, (4) PR celebration animation, (5) Progress charts, (6) Coach-client messaging

## 8.2 Marketing Launch (Weeks 18–20)

Launch Week Sequence

- Day 1: Email blast to waitlist + social media announcement

- Day 2: Product Hunt launch (schedule for Tuesday 12:01 AM PST)

- Day 3: Ambassador coaches publish review posts/videos

- Day 4–5: Reddit posts in r/crossfit, r/personaltraining, r/fitness

- Day 5–7: Apple Search Ads campaign begins ($50–100/day)

Ongoing Channels

- Content marketing: 2 blog posts/week targeting coach SEO keywords

- Instagram/TikTok: daily short-form content (coach workflow tips, feature demos, athlete transformations)

- Ambassador program: 20–50 coaches with free Pro accounts + referral commissions

- CrossFit affiliate outreach: email/visit local boxes offering 30-day free trials

- Apple Search Ads: $1,000–3,000/month targeting coaching and CrossFit keywords

## 8.3 V1.1 Features (Weeks 20–24)

Based on beta feedback prioritization, begin building the next tier of features:

| Priority | Feature | Value | Effort |
| --- | --- | --- | --- |
| P0 | Group leaderboards with reactions/fist bumps | Community engagement — the #1 requested CrossFit feature | 2 weeks |
| P0 | Apple Health / Google Fit sync | Table stakes for App Store credibility | 1 week |
| P1 | Multiple programming tracks per gym (Competitors / Fitness / Foundations) | Serve box owners with diverse member levels | 1.5 weeks |
| P1 | RPE/RIR logging alongside weight/reps | Advanced athlete tracking | 3 days |
| P2 | Pre-workout wellness check-in (sleep, stress, soreness) | Inform coach programming decisions | 1 week |
| P2 | Program marketplace (coach sells templates) | Revenue diversification for coaches | 3 weeks |
| P2 | AI workout suggestions based on logged history | Differentiator — leverage pgvector + embeddings | 2 weeks |

# 9. Testing Strategy

AI-assisted development requires a strong testing foundation to catch regressions that AI edits can introduce.

| Layer | Tool | What It Tests | When It Runs |
| --- | --- | --- | --- |
| Type checking | TypeScript strict mode | Type safety across entire codebase | Every save (IDE) + CI |
| Unit tests | Vitest | Business logic, utility functions, Zod schemas | CI on every PR |
| Component tests | React Native Testing Library | Component rendering, user interactions | CI on every PR |
| API tests | Supabase local + pgTAP | RLS policies, database triggers, edge functions | CI on every PR |
| E2E tests | Maestro | Critical user flows on real devices/simulators | EAS Workflows nightly |
| Performance | Flashlight (mobile perf) | Frame rate, startup time, memory leaks | Weekly benchmark |
| Crash reporting | Sentry + Firebase Crashlytics | Production crashes with source maps | Always on |

# 10. Cost Breakdown by Phase

## 10.1 Development Tools (Monthly)

| Tool | Purpose | Cost |
| --- | --- | --- |
| Claude Code (Max 5x plan) | AI-assisted development | $100/mo |
| Cursor Pro | IDE with AI features | $20/mo |
| Apple Developer Program | iOS distribution | $99/yr (~$8/mo) |
| Google Play Console | Android distribution | $25 one-time |
| GitHub Pro | Repo hosting, Actions CI | $4/mo |
| Expo EAS Starter | Cloud builds + OTA updates | $19/mo |
|  | TOTAL DEV TOOLS | ~$151/mo |

## 10.2 Infrastructure (Monthly at Launch)

| Service | Tool | Cost |
| --- | --- | --- |
| Backend + Database | Supabase Pro | $25–75 |
| Web hosting | Vercel Pro | $20 |
| Video hosting | Bunny.net Stream | $5–15 |
| Push notifications | Expo Push (included) | $0 |
| Analytics | PostHog free tier | $0 |
| Crash reporting | Sentry free + Crashlytics | $0 |
| Subscriptions | RevenueCat (<$2.5K MTR) | $0 |
| Email | Resend free tier | $0 |
|  | TOTAL INFRASTRUCTURE | $50–110/mo |

## 10.3 Pre-Launch One-Time Costs

| Item | Cost | Notes |
| --- | --- | --- |
| LLC formation | $100–500 | State-dependent; Delaware recommended for future VC |
| Privacy Policy + ToS (lawyer review) | $500–1,500 | Template + attorney review for health data compliance |
| General liability insurance | $500–1,000/yr | Required for coaching platform liability |
| Logo + brand assets | $0–500 | DIY with Figma or hire freelancer |
| App Store screenshots | $0–200 | DIY with Figma templates or hire |
|  | TOTAL ONE-TIME | $1,100–3,700 |

# 11. Risk Mitigation

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| App Store rejection (health data) | Medium | High | Complete all health declarations pre-submission; separate health privacy policy; no health data used for ads |
| Coach workout builder too complex | High | High | Start with freeform text + structured overlay; don’t force rigid templates. Beta test with 10 coaches before building more structure |
| Offline sync conflicts | Medium | Medium | Client-wins for logged data, server-wins for templates. Conflict UI shows diff for manual resolution |
| AI code quality regression | Medium | Medium | Strong ESLint rules as guardrails, TypeScript strict mode, Maestro E2E tests catch regressions, code review every PR |
| Low beta conversion | Medium | High | Founders pricing lock-in, 30-day trial, weekly check-ins with beta coaches, iterate on top 3 friction points |
| Competitor copies CrossFit features | Low | Medium | Speed to market is the moat; community and brand loyalty take time to replicate; keep shipping V1.1+ features monthly |

# 12. Success Metrics

## 12.1 Launch Targets (First 90 Days)

| Metric | Target | How Measured |
| --- | --- | --- |
| Coaches signed up | 100 | Supabase users table (role = coach) |
| Active clients | 500 | Clients who logged ≥1 workout in past 7 days |
| Daily active users (DAU) | 200 | PostHog daily active events |
| Workout log rate | >60% of assigned workouts logged | logged_workouts / assigned_workouts |
| Coach retention (30-day) | >70% | Coaches active at day 30 / coaches signed up |
| App Store rating | ≥4.5 stars | App Store Connect / Play Console |
| Monthly recurring revenue | $2,000 | RevenueCat dashboard |
| NPS score | >50 | In-app survey at day 14 |

## 12.2 Key Insight from Research

Users who regularly view progress data have 2.3× higher retention rates. This means the Track tab (progress charts, PR history, compliance rates) isn’t a nice-to-have — it’s a retention engine. Invest in making progress data beautiful and instantly accessible.

# 13. Immediate Next Steps

To begin development this week:

- Install Claude Code CLI and Cursor IDE. Set up Anthropic API key.

- Create the monorepo: npx create-expo-app@latest train-track, configure Turborepo + pnpm workspaces.

- Create Supabase project. Run initial migration with core schema (users, coach_clients, programs, workout_templates, exercises).

- Write CLAUDE.md with the 7 critical rules from Section 3.1.

- Build authentication flow: sign up (with role selection), sign in, password reset.

- Build coach navigation shell with sidebar. Build client navigation shell with bottom tabs.

- Begin the workout builder — start with Straight Sets format, then add AMRAP and For Time.

The prototype JSX file (TrainTrack.jsx) and the application specification document (Train_Track_Application_Specification.docx) should be provided to Claude Code as reference context when building each feature. The prototype defines the visual design; this document defines the architecture and implementation requirements.